## Slide 1: Project TIME Management
Dr. Uzair Iqbal, CS Dept., CIIT, Islamabad
The content mainly based on the PMBOK guide, 5th edition; and Software extension to the PMBOK guide, PMI, 2013.
Notes: NOTE:
To change the image on this slide, select the picture and delete it. Then click the Pictures icon in the placeholder to insert your own image.

## Slide 2: Introduction [1/3]
Project time management for software projects is driven by risk, resource availability, business value, and the scheduling method(s) used
  Understanding and selection of scheduling methods is critical
Software project schedule should remain ﬂexible throughout the project
Most of the development cost of software project is human effort
  Effort: the product of people and time
Value delivered to the customer is an important factor

## Slide 3: Introduction [2/3]
Scheduling methods
  Structured scheduling
    Well understood product requirements, related precedent work within the organization
    High safety, security, or regulatory constraints
  Schedule as independent variable (SAIV)
    Specific date to deliver the product; otherwise the sharp decline of product value
    Similar to “time boxing” in adaptive life cycles
  Iterative scheduling with a backlog
    Rolling wave planning for software projects based on adaptive life cycles
    Adjustment to an iterative scheduling occur throughout the project life cycle

## Slide 4: Introduction [3/3]
Scheduling methods
  On-demand scheduling
    Based on the theory-of-constraints and pull-based scheduling
    No pre-scheduling
    Minimize estimation activities and maximize the value of work accomplished
  Portfolio management scheduling
    Scheduling of projects based on prioritizing investments in software as established by criteria determined at the organizational level

## Slide 8: Introduction [3/3]
Plan Schedule Management
Define Activities
Sequence Activities
Estimate Activity Resources
Estimate Activity Durations
Develop Schedule
Control Schedule

## Slide 9: Process 1: Plan Schedule Management
The process of establishing the policies, procedures, and documentation for planning, developing, managing, executing, and controlling the project schedule.
Guidance and direction on how the project schedule will be managed
Formal/informal, highly detailed or broadly framed
How schedule contingencies will be reported and assessed
Plan may be updated to reflect the change
Figure source: Software Extension to PMBOK® Guide – Fifth Edition, PMI, 2013, pp. 90

## Slide 10: Plan Schedule Management: Inputs [1/2]
Project management plan
  Scope baseline
    scope statement and work breakdown structure (WBS)
  Other information
    cost, risk, and communications decisions
Project charter
  summary milestone schedule and project approval
Enterprise environmental factors
  Organizational culture and structure can all inﬂuence schedule management
  Resource availability and skills that may inﬂuence schedule planning
  Project management software provides the scheduling tool and alternative possibilities for managing the schedule
  Published commercial information, such as resource productivity information, is often available from commercial databases that track
  Organizational work authorization systems
  Software project portfolios
  Enterprise architectures

## Slide 11: Plan Schedule Management: Inputs [2/2]
Organizational process assets
  Monitoring and reporting tools to be used
  Historical information
  Schedule control tools
  Existing formal and informal schedule control related policies, procedures, and guidelines
  Templates
  Project closure guidelines
  Change control procedures
  Risk control procedures
Safety and Security Issues
  Public safety and cyber security issues
  safety and security regulations, standards, policies, and requirements

## Slide 12: Plan Schedule Management: Tools and Techniques
Expert judgment
  Expertise in an application area, knowledge area, industry etc.
Analytical techniques
  scheduling methodology, scheduling tools and techniques, estimating approaches, formats, and project management software
Meetings
  project manager, project sponsor, selected project team members, selected stakeholders, anyone with responsibility for schedule planning or execution, and others as needed

## Slide 13: Plan Schedule Management: Outputs
Schedule management plan
  Project schedule model development
  Level of accuracy
  Units of measure
  Organizational procedures links
  Project schedule model maintenance
  Control thresholds
  Rules of performance measurement
  Reporting formats
  Process descriptions

## Slide 14: Process 2: Define Activities
The process of identifying and documenting the specific actions
A basis for estimating, scheduling, executing, monitoring the work
Figure source: Software Extension to PMBOK® Guide – Fifth Edition, PMI, 2013, pp. 90

## Slide 15: Define Activities: Inputs
Schedule management plan
Scope baseline
  Organization’s enterprise architecture
Enterprise environmental factors
  Organizational cultures and structure
  Published commercial information from commercial databases
  Project management information system (PMIS)
Organizational process assets
Additional factors
  Existing work orders and enhancement requests; technical debt remaining from previous work, incomplete functionality, and needed rework; business process changes; and activities external to a software project such as database or operating system upgrades

## Slide 16: Define Activities: Tools and Techniques
Decomposition
  Dividing the project scope and deliverables into smaller, more manageable parts
  Work packages in WBS are decomposed into activities
  Activities represent the effort needed to complete a work package.
Rolling wave planning
Expert judgment
Story breakdown structure
  User stories
    Epic and themes
  Procurement, documentation, risk management etc. based on stories
Storyboards
Use cases

## Slide 17: Define Activities: Outputs [1/2]
Activity list
  Comprehensive list of all schedule activities having identifier and scope of work
  Coordination with entities external
Activity attributes
  Multiple components associated with an activity
  Activity identifier (ID), WBS ID, activity label, activity codes, activity description, predecessor activities, successor activities, logical relationships, leads and lags, resource requirements, imposed dates, constraints, and assumptions
  Dependencies and enabling precedent activities
  Stakeholder value or priority
  Estimated effort, size, complexity, and/or risk
  Security and/or safety standards and constraints
  Special competencies required of project team members and others

## Slide 18: Define Activities: Outputs [2/2]
Milestone list
  Milestone is a significant point or event in a project
  List contains all milestones of a project
  Mandatory or optional
  Zero duration
  Anchor points in software development life cycle
  Predictive software development: requirements and architectural design reviews, customer reviews, and product delivery
  On-demand scheduling methods: no milestones, customer satisfaction
  Define joint milestones with interdependent projects to reduce project risk

## Slide 19: Process 3: Sequence Activities
Process of identifying and documenting relationships among the activities
The logical sequence of work to obtain the greatest efficiency
Software projects are different in nature
  Dependencies on database structure and infrastructure needs etc.
  Establish and refine the operational concepts, to build prototypes, to define architecture
  Depends on the familiarity, size, and complexity of the software product
  Software architecture has a significant impact
  Software schedules are frequently revised
    Unscheduled prototyping, code experimentation, “dark matter”
Figure source: Software Extension to PMBOK® Guide – Fifth Edition, PMI, 2013, pp. 90

## Slide 20: Sequence Activities: Inputs
Schedule management plan
Activity list
Activity attributes
Milestone list
Project scope management
Enterprise environmental factors
Organizational process assets

## Slide 21: Sequence Activities: Tools and Techniques [1/4]
Precedence Diagramming Method (PDM)
  Activities represented as nodes and are linked by logical relationships
  Activity-on-Node (AON)
  Types of dependencies / logical relationship
    Finish-to-start (FS)
      Award ceremony cannot start until the race has finished
    Finish-to-finish (FF)
      Document writing is required to finish before editing the document can finish
    Start-to-start (SS)
      Level concrete cannot begin until pour foundation begins
    Start-to-finish (SF)
      The first security guard shift cannot finish until the second security guard shift starts
Figure source: PMBOK® Guide – Fifth Edition, PMI, 2013, pp. 157

## Slide 22: Sequence Activities: Tools and Techniques [2/4]
Dependency determination
  Mandatory dependencies
    Hard logic, hard dependencies
    Legal, contractual, or inherent
  Discretionary dependencies
    Preferred logic, preferential logic, soft logic
    Based on knowledge of best practices
    Should be fully documented
  External dependencies
    Relationship between project and non-project activities
  Internal dependencies
    Precedence relationship between project activities

## Slide 23: Sequence Activities: Tools and Techniques [3/4]
Leads and lags
  Lead
    The amount of time whereby a successor activity can be advanced with respect to a predecessor activity
    Represented as a negative value for lag
  Lag
    The amount of time whereby a successor activity will be delayed with respect to a predecessor activity
  Activities and their related assumptions should be documented
Figure source: PMBOK® Guide – Fifth Edition, PMI, 2013, pp. 158

## Slide 24: Sequence Activities: Outputs
Project schedule network diagrams
  Graphical representation
  Description should be associated for unusual sequence
Project documents updates
  Activity lists and attributes, milestone list, and risk register
Features sets
Release plans
  The overall project schedule of releases
  Dependent on the production of the software team
Architectural and nonfunctional dependencies
Figure source: PMBOK® Guide – Fifth Edition, PMI, 2013, pp. 160

## Slide 25: Process 4: Estimate Activity Resources
Estimating the type and quantities of material, people, equipment, or supplies
Identification of the type, quantity, and characteristics of resources required
More accurate cost and duration estimates
The skills and abilities of software developers are significant factors
Figure source: Software Extension to PMBOK® Guide – Fifth Edition, PMI, 2013, pp. 90

## Slide 26: Estimate Activity Resources: Inputs
Schedule management plan
Activity list
Activity attributes
Resource calendars
Risk register
Activity cost estimates
Enterprise environmental factors
  Resource location, availability, and skills
Organizational process assets

## Slide 27: Estimate Activity Resources: Tools and Techniques
Expert judgment
Alternative analysis
Published estimating data
Bottom-up estimating
Project management software
Service-level agreements
Other tools and techniques
  Algorithmic estimation models
  Function point/story point/use-case estimation tools

## Slide 28: Estimate Activity Resources: Outputs
Activity resource requirements
  Types and quantities of resources required
Resource breakdown structure
  Hierarchical representation of resources
  Resource categories: labor, material, equipment, and supplies etc.
  Resource types: skill level and grade level etc.
Project documents updates
  Activity list and attributes, resource calendars

## Slide 29: Process 5: Estimate Activity Durations
Estimating the number of work periods needed to complete activities
Factors affecting estimates in software projects
  Intangibility of software
  Broad variance in productivity of software developers
  Need for changes to meet emergent requirements
  The often unprecedented nature of the software product
  Unknown competencies of the software team
  Unknown hardware or software defects
  The need to incorporate other software (legacy, commercial, open-source etc.)
Figure source: Software Extension to PMBOK® Guide – Fifth Edition, PMI, 2013, pp. 90

## Slide 30: Estimate Activity Durations: Inputs
Schedule management plan
Activity list
Activity attributes
Activity resource requirements
Resource calendars
Project scope statement
Risk register
Resource breakdown structure
Enterprise environmental factors
Organizational process assets
Additional inputs
  Customer stories and features organized into lists, groups, or sets
  Velocity and rework metrics

## Slide 31: Estimate Activity Durations: Tools and Techniques [1/2]
Expert judgment
Analogous estimating
Parametric estimating
Three-point estimating
  Program Evaluation and Review Technique (PERT)
    Most likely (tM): the average case scenario
    Optimistic (tO): the best case scenario
    Pessimistic (tP): the worst case scenario
    Triangular distribution. tE = (tO + tM + tP) / 3
    Beta distribution (from the traditional PERT technique). tE = (tO + 4tM + tP) / 6
Bottom Up Estimation

## Slide 32: Estimate Activity Durations: Tools and Techniques [2/2]
Group decision-making techniques
  Voting
    Fist to five
Reserve analysis
  Contingency reserves
    “Known-unkowns”
    a percentage of the estimated activity duration, a fixed number of work periods, or may be developed by using quantitative analysis methods such as Monte Carlo simulation
    May be used, reduced, or eliminated based on more precise information
    Included in schedule documentation
  Management reserves
    Withheld for management control purposes
    “Unknown unkowns”
    Not included in schedule baseline

## Slide 33: Estimate Activity Durations: Outputs
Activity duration estimates
  Quantitative assessment of time required to complete the activity
  Lags are not included
  Range of time e.g. 2 week + 2 days or 15% probability of exceeding three weeks
Project documents updates
  Project documents that may be updated include, but are not limited to:
    Activity attributes; and
    Assumptions made in developing the activity duration estimate, such as skill levels and availability, as well as a basis of estimates for durations.

## Slide 34: Process 6: Develop Schedule
Process of analyzing activity sequences, durations, resource requirements, and schedule constraints to create the project schedule model
Iterative process
Different presentation forms of project schedules are possible
Software project schedules and plans change
  Customer requests
  Project feedback
  The emergence of previously unidentified work activities
Figure source: Software Extension to PMBOK® Guide – Fifth Edition, PMI, 2013, pp. 90

## Slide 35: Develop Schedule: Inputs [1/2]
Schedule management plan
Activity list
Activity attributes
Project schedule network diagrams
Activity resource requirements
Resource calendars
Activity duration estimates

## Slide 36: Develop Schedule: Inputs [2/2]
Project scope statement
Risk register
Project staff assignments
Resource breakdown structure
Enterprise environmental factors
Organizational process assets
Additional inputs

## Slide 37: Develop Schedule: Tools and Techniques [1/5]
Activity/Task | Duration | Precedence
A | 5 | --
B | 5 | A
C | 10 | A
D | 15 | B,C
1 | 5 | 5
A |  | 
1 | 0 | 5

## Slide 38: Develop Schedule: Tools and Techniques [1/6]
Schedule network analysis
Critical path method
  Estimate the minimum project duration and determine the amount of scheduling ﬂexibility on the logical network paths within the schedule model
  Calculates the early start, early finish, late start, and late finish dates for all activities
  The longest path is the critical path
  The shortest possible project duration
  Critical path is normally characterized by zero total ﬂoat
  Activity on the critical path: critical path activity
  Free float: free time that an activity can be delayed
  without delaying the early start date of any successor
Figure source: PMBOK® Guide – Fifth Edition, PMI, 2013, pp. 177

## Slide 39: Develop Schedule: Tools and Techniques [2/5]
Critical chain method
  Inclusion of buffers on any project schedule path
  Critical chain: resource-constrained critical path
  Buffer: non-work schedule activity
  Project buffer: at the end of the critical path
  Feeding buffer: at the entry point at the critical path
Figure source: PMBOK® Guide – Fifth Edition, PMI, 2013, pp. 178

## Slide 40: Develop Schedule: Tools and Techniques [3/5]
Resource optimization techniques
  Resource leveling
    Adjusting start and end dates to balance resources demand
    Availability of shared or critically required resource at certain times
    Cause the original critical path to change, usually to increase
  Resource smoothing
    Adjusting the activities to not exceed predefined resource limits
    Critical path is not changed
    Activities are delayed within their free and total float
Figure source: PMBOK® Guide – Fifth Edition, PMI, 2013, pp. 179

## Slide 41: Develop Schedule: Tools and Techniques [4/5]
Modeling techniques
  What-if scenario analysis
    Evaluating scenarios to predict their effect on project objectives
    Assess the feasibility of the project schedule under adverse conditions
  Simulation
    Calculating multiple project durations with different sets of activity assumptions
    Monte Carlo analysis
Leads and lags
Resource Leveling and Resource Smoothing

## Slide 42: Develop Schedule: Tools and Techniques [5/5]
Schedule compression
  Shorten the schedule duration without reducing the project scope
  Crashing
    Add resources by the least incremental cost
    Overtime, additional resources, quick payments
    Not necessarily better alternative
  Fast tracking
    Activities are performed in parallel rather than in sequence
    May result in rework and increased risk
  Software projects rarely succeed when the project schedule is compressed more than 25%
  Brooks law: “adding manpower to a late project makes it later.”
  For adaptive software projects: reduce the features planned or less functionality within a feature
Scheduling tool
Incremental product planning

## Slide 43: Develop Schedule: Outputs [1/2]
Schedule baseline
  The approved version of a schedule
Project schedule
  Master/milestone schedule
  Different presentation forms
    Bar charts (Gantt charts)
    Milestone charts
    Project schedule network diagrams
Schedule data
  Schedule milestones, schedule activities, activity attributes, and documentation of all identified assumptions and constraints
  Resource requirements by time period, often in the form of a resource histogram
  Alternative schedules, such as best-case or worst-case, not resource-leveled, or resource-leveled, with or without imposed dates
  Scheduling of contingency reserves

## Slide 44: Develop Schedule: Outputs [2/2]
Project calendars
  Identification of working days and shifts for scheduled activities
Project management plan updates
Project documents updates
Release and iteration plan udpates

## Slide 45: Process : Control Schedule
Challenging task to control the schedule
  Determining the current status of the project schedule
  Inﬂuencing the factors that create schedule changes
  Determining if the project schedule has changed
  Managing the actual changes as they occur
Factors that affect software project schedule
  The rate that teams are delivering completed software increments
  The current rate of completion for work in process
  The risks and dependencies that can impact the schedule
  The impact of technical variance on the schedule
  Options for reprioritizing product scope
Figure source: Software Extension to PMBOK® Guide – Fifth Edition, PMI, 2013, pp. 90

## Slide 46: Control Schedule: Inputs
Project management plan
Project schedule
Work performance data
Project calendars
Schedule data
Organizational process assets
  Existing formal and informal schedule control-related policies, procedures, and guidelines
  Schedule control tools
  Monitoring and reporting methods to be used

## Slide 47: Control Schedule: Tools and Techniques [1/2]
Performance reviews
  Trend analysis
  Critical path method
  Critical chain method
  Earned Value Management (EVM)
  Technical review cycle
Project management software
Resource optimization techniques
Modeling techniques
Leads and lags
Schedule compression
Schedule tool

## Slide 48: Control Schedule: Tools and Techniques [2/2]
Evidence-based reviews
Retrospectives
Cumulative flow diagrams
Workflow board with daily walkthrough
Reprioritization reviews
Burnup and burndown charts
Variance analysis
Figure source: Software Extension to PMBOK® Guide – Fifth Edition, PMI, 2013, pp. 115

## Slide 49: Control Schedule: Outputs
Work performance information
Schedule forecasts
Change requests
Project management plan updates
Project documents updates
Organizational process assets updates
Additional outputs

## Slide 50
https://www.tutorialspoint.com/management_concepts/leads_lags_floats.htm
https://pmstudycircle.com/2013/02/lead-time-and-lag-time-in-project-scheduling-network-diagram/
https://pmstudycircle.com/2014/02/critical-chain-method-ccm-in-project-management/

## Slide 51
EXTRA

## Slide 56: Project Buffer
This buffer is placed between the last task and the project completion date as a non-activity buffer, and this buffer acts as a contingency for the critical chain activities.
Any delay on the critical chain will eat this buffer, but the project completion date will remain unchanged. Also, if there is any gain from the early finish of any activity, this gain will be added to this buffer as well.
Usually the duration of this buffer is 50% of the contingency that you have removed from each task estimate. This helps you move uncertainty from each task to the project buffer.
Please note that, although the critical chain starts from the beginning, it ends before the start of the project buffer. It does not end at the end of the project. This duration will include any time duration borrowed from the project buffer or exclude the duration added to the buffer

## Slide 57: Feeding Buffers
These buffers are added to the non-critical chain so that any delay on the non-critical chain does not affect the critical chain.
They are inserted between the last task on a non-critical chain and the critical chain.
Feeding buffers are also calculated the same way as the project buffer.
The duration of these buffers is based on some fraction of the safety removed from the tasks on non-critical chains.

## Slide 58: Resource Buffer
These buffers are kept alongside the critical chain to make sure that they are available when they are required.
This buffer can be a human resource or any equipment.
Please note that, since the critical chain considers the resource constraints as well, it may be longer than the critical path schedule.
However, this might be compensated by removing the contingencies from the activities. Resources used in critical chain are known as critical resources

## Slide 59: Difference Between Buffer and Float (or Slack)
Float or slack is a critical path phenomenon, and buffer belongs to critical chain.
Float is the difference between the duration of the critical path and non-critical path. On a critical path, float is zero.
Buffer is based on contingencies. For example, the project buffer is about 50% of the safety time that you have removed from the activity estimate duration. As per the definition of buffer, it is not zero on a critical chain or any other chain.

## Slide 60: Difference Between Buffer and Float (or Slack)
Float is the same for all activities on a non-critical path, any activity can consume it partially or fully, and balance can be utilized by other activities. There is no further analysis.
Buffer can also be borrowed by any activity if the activity is delayed. The project manager analyzes the remaining buffer to find the status of the project.
Buffer can be divided into three categories: project buffer, feeding buffer and resource buffer. Float can be either total float or free float.

## Slide 61: PERT – Program Evaluation and Review Technique
PERT is a statistical tool that is widely used in project management for developing the project schedule for very large, complex, and one time projects where usually no historical records are available to be reviewed
At first glimpse, you may think that PERT Diagram Method is similar to the critical path method; however, there are many differences between these two techniques, such as:

## Slide 62: PERT – Program Evaluation and Review Technique
Critical Path Method (CPM) is activity oriented, while PERT is event oriented
Critical Path Method is used when you have definitive time estimate, while in PERT there is no certainty in time estimate
In CPM diagram, activity is shown on the node, while in PERT Diagram, activity is shown on the arrow, and nodes represent the milestones. (Therefore, PERT diagrams are also known as Activity on Arrow (AOA) diagram)
PERT Diagram can only have a “Finish to Start” type of relationship, while the CPM method can have any type of dependency; e.g. Start to Finish, Finish to Start, etc.
In CPM diagram, rectangles represent the nodes. In PERT diagram, circles represent nodes

## Slide 63
PERT methodology is used mainly on very large and complex projects where time is a more important factor than the cost.
PERT is mainly used in research type projects where you cannot predict the time duration of any activity accurately; therefore, you have to plan your work based on the milestones.
The critical path method is a deterministic model where you use a fixed time estimate for activities.
CPM (critical path method) helps you run the project efficiently if the time estimates are definitive; however, if there is a variation in time estimate, it may affect your project badly.
The solution to this drawback of the CPM method is built into the PERT methodology, which helps you complete project successfully with less cost and time.

## Slide 64: ACTIVITY ON ARROW
Task | Precedence | Duration
A | --------- | 3
B | --------- | 4
C | B | 7
D | A | 5
E | C | 2

## Slide 66
Normal Activity
Fast Tracking
Crashing
1 | 2 | 3 | 4 | 5 | 6
7 | 8 | 9 | 10 | 11 | 12
13 | 14 | 15 | 16 | 17 | 18
1 | 2 | 3 | 4 | 5 | 6
5 | 6 | 7 | 8 | 9 | 10
9 | 10 | 11 | 12 | 13 | 14
1 | 2 | 3
4 | 5 | 6 | 7
8 | 9 | 10
High Risk
High COST

## Slide 72: Must Go through
https://pmstudycircle.com/2014/01/critical-path-method-cpm-in-project-management/
https://pmstudycircle.com/2013/03/total-float-versus-free-float/