Critical Path Model (CPM) – Easy Study Notes

## 📌 What is CPM?

CPM (Critical Path Method) is used in project management to:

- Visualize all project tasks (activities)

- Find the longest path (critical path) through the tasks

- Figure out the shortest time to complete the project

- Know which tasks must not be delayed

## 🧭 Network Diagrams – Foundations

Think of it as drawing a map of your project. It shows:

- Tasks (called activities)

- Which task depends on which

- When each task can start or finish

### 🔄 Dependency Types:

| Dependency | What it means | Real-life example |
| --- | --- | --- |
| FS (Finish-to-Start) | Task B starts after A finishes | You cook dinner after buying groceries |
| SS (Start-to-Start) | Task B starts after A starts | You can start ironing clothes once the washing starts |
| FF (Finish-to-Finish) | Task B finishes after A finishes | Two friends finishing separate assignments together |
| SF (Start-to-Finish) | Task B finishes after A starts (rare) | A night shift worker must leave only after the morning shift arrives |

## 🧱 Notations for Diagrams

### 1. Arrow Diagramming Method (ADM)

- Arrows = tasks

- Circles = milestones/events

- Used more for historical or simpler cases

### 2. Precedence Diagramming Method (PDM) 🔥 Most used

- Boxes = tasks

- Arrows = dependencies

- Supports FS, SS, FF, SF types

## 🔑 Key Concepts

### 🔗 Path:

- A chain of tasks from start to end.

### 🔴 Critical Path (CP):

- The longest duration path through the network.

- It shows the minimum time the project will take.

- Any delay here = project delay.

### 🔥 Critical Activities:

- Tasks on the CP

- Total Float (TF) = 0

- Must be done on time

### ⏳ Float (Slack):

- The amount of time a task can be delayed without delaying something else.

#### Types of Float:

| Type | What it means |
| --- | --- |
| Total Float (TF) | Delay without affecting project end date |
| Free Float (FF) | Delay without affecting next task's start |

## 🧮 How to Find the Critical Path

- Draw the full network (all tasks + dependencies)

- List all paths from Start to End

- Add durations of tasks in each path

- The path with the highest total = Critical Path

- This path has TF = 0

### ✅ Example:

Paths and their durations:

- Start → A → B → C → End = 31 days ✅ (CP)

- Start → D → E → F → End = 18 days

- Start → D → B → C → End = 26 days

- Start → G → H → I → End = 13 days

### 🎯 Floats:

- TF of D–E–F = 31 − 18 = 13 days

- TF of G–H–I = 31 − 13 = 18 days

## ⏩ Forward Pass (Early Dates)

Used to find Earliest Start (ES) and Earliest Finish (EF) for each task.

### 🔑 Formulas:

- ES = EF of predecessor + 1

- EF = ES + Duration − 1

## ⏪ Backward Pass (Late Dates)

Used to find Latest Start (LS) and Latest Finish (LF).

### 🔑 Formulas:

- LF (last task) = EF (from CP)

- LS = LF − Duration + 1

- LF of previous task = LS of successor − 1

## 🧠 Critical Path Property

For critical tasks:

- ES = LS

- EF = LF

👉 This confirms there's no flexibility (TF = 0).

## 💡 Example Breakdown

Path: D → E → F

- Project ends at day 31

- F duration = 6 → LF = 31 → LS = 26

- E duration = 7 → LF = 25 → LS = 19

- D has 2 successors → use earlier LS (choose min(11,19))

- So, LF(D) = 10 → LS(D) = 6

## 🧾 Float (Slack) Calculation

### Total Float (TF):

- TF = LF − EF = LS − ES

- Or use: TF = CP duration − Path duration

### Free Float (FF):

- FF = ES of successor − EF of current task − 1

### 🎯 Example: 2 Paths

- A → B → D = 20 days (Critical)

- A → C → D = 12 days

- TF for C = 20 − 12 = 8 days

- FF for C = ES of D − EF of C − 1 = 16 − 7 − 1 = 8

### ⛓️ Converging Example

If two paths merge at E (from D and G), only one gets FF — the one that lets E start earlier.

## 💡 Benefits of CPM

- Clear visual of project flow

- Makes dependencies and bottlenecks obvious

- Helps with planning, scheduling, and control

- Helps manage delays and risk with float info

- Shows where to focus management attention

## ⚠️ Limitations of CPM

- Assumes unlimited resources (not realistic)

- Doesn’t consider staff/equipment limits

- People may abuse float and delay tasks on purpose

- Non-critical tasks might become critical later

- Still fails in real life if resources or human factors ignored

👉 Solution: Critical Chain Method (CCM)
Adds:

- Resource limits

- Buffers to absorb delays

## 📝 Exam Tips

✅ Memorize these:

- Forward Pass: ES = EFprev + 1, EF = ES + Dur − 1

- Backward Pass: LS = LF − Dur + 1, LF = LSsucc − 1

- TF = LF − EF or CP duration − path duration

- FF = ESsucc − EFcurr − 1

⚠️ Always:

- Use earliest LS if activity has multiple successors

- Know: TF = 0 ⇒ Critical Activity

- FF gives local flexibility (won’t delay successor)

- TF affects whole project deadline

💡 Compare CPM vs. CCM in theory questions
Use real-world logic: if workers are limited, CPM alone won’t work.