Project Time Management

### Conceptual Overview of Project Time Management

- The goal is to plan, manage, and control the project schedule so the project finishes on time and brings maximum value.

- Especially in software projects, most costs come from human effort.

  - Effort = People × Time

    - Example: If 3 developers work for 4 weeks, total effort = 3 × 4 = 12 person-weeks.

- Software has unique challenges:

  - Outputs (like code) are intangible – not easily seen or measured.

  - Requirements change frequently (called volatility).

  - Technical debt (quick fixes today = bigger problems later).

  - New, innovative work with no prior references.

- These make accurate time estimates very difficult.

- Instead of fixed schedules, software projects use flexible, adaptive schedules (e.g., Agile).

- Missing deadlines can kill product value (e.g., missing a Christmas app release window).

### Scheduling Methods for Software Projects

- Structured Scheduling

  - Used when requirements are clear and strict (e.g., medical software).

  - Focuses on detailed upfront planning and strict timelines.

- Schedule as Independent Variable (SAIV)

  - Fixed deadline, no matter what.

  - Scope or resources are adjusted to meet the date.

  - Example: App must launch before a global sports event.

- Iterative Scheduling with a Backlog

  - Used in Agile. Work is broken into sprints (2–4 weeks).

  - Priorities can change each sprint based on customer feedback.

  - The backlog is a list of features/tasks, updated regularly.

- On-Demand Scheduling (Kanban)

  - No fixed schedule; tasks are pulled only when there's room.

  - Focuses on flow, not fixed timelines.

  - Example: Support tickets handled as they come in, without overloading the team.

- Portfolio-Level Scheduling

  - Managing multiple projects across the company.

  - Decides which project gets what resources, based on company goals.

### PMBOK Time-Management Process Map (Software Focus)

| Process Number | Name |
| --- | --- |
| 6.1 | Plan Schedule Management |
| 6.2 | Define Activities |
| 6.3 | Sequence Activities |
| 6.4 | Estimate Activity Resources |
| 6.5 | Estimate Activity Durations |
| 6.6 | Develop Schedule |
| 6.7 | Control Schedule |

These processes connect with other areas like project risk, scope, and the project charter.

### Process 1 – Plan Schedule Management

Goal: Create a Schedule Management Plan (SMP) – a guide for how scheduling will be done.

Inputs:

- Project Charter & Management Plan (includes WBS and risk plan)

- EEFs (e.g., company tools, working culture)

- OPAs (e.g., past project templates, company rules)

Tools:

- Expert advice

- Analytical methods (e.g., choosing Agile vs Waterfall)

- Meetings with team/stakeholders

Output: A detailed SMP that includes:

- Scheduling method (e.g., Agile)

- Accuracy levels (e.g., use days, not hours)

- Company process links

- Maintenance plan (how schedule will be updated)

- Control limits (how much delay is acceptable)

- Rules for measuring progress (e.g., EVM)

- Report formats and who receives them

### Process 2 – Define Activities

Goal: List all the tasks needed to complete the project.

Inputs:

- Schedule plan

- Scope baseline (especially the WBS)

- Technical constraints (e.g., certain tools must be used)

- Technical debt, external updates (e.g., database upgrade)

Tools:

- Decomposition – break down WBS into small tasks

- Rolling-wave planning – plan near-term in detail, future in rough outline

- Agile tools – stories, epics, use cases

- Expert judgment

Outputs:

- Activity List – all the tasks with IDs and descriptions

- Activity Attributes – extra info: dependencies, constraints, effort needed

- Milestone List – major events (e.g., beta release). Some are fixed, others flexible.

### Process 3 – Sequence Activities

Goal: Decide the right order to do the tasks.

Inputs:

- Activity lists, attributes, milestones, SMP

Tools:

- Precedence Diagramming Method (PDM):

  - FS (Finish to Start): Coding must finish before testing starts

  - FF: Requirements must finish before testing finishes

  - SS: Design and coding start at the same time

  - SF (rare): New system starts before the old one ends

- Dependency Types:

  - Mandatory: Must be done in order (e.g., paint must dry before another coat)

  - Discretionary: Best practice, but not required (e.g., review before coding)

  - External: Outside the project (e.g., waiting for hardware delivery)

  - Internal: Within project team control

- Leads & Lags:

  - Lead: Start next task early (e.g., documentation starts before coding ends)

  - Lag: Delay between tasks (e.g., wait 5 days after concrete pour)

Outputs:

- Schedule Network Diagram – flowchart of task order

- Project Document Updates – adjust risks, plans, etc.

### Process 4 – Estimate Activity Resources

Goal: Figure out what people, tools, and materials are needed for each task.

Inputs:

- Schedule Plan, Activity List, Resource Calendar, Risk Register

Tools:

- Expert judgment

- Alternative analysis (e.g., hire expert vs train intern)

- Published data (industry benchmarks)

- Bottom-up estimating (most accurate)

- PM Software

- SLAs (e.g., cloud service availability terms)

- Algorithmic models (e.g., story points for coding)

Outputs:

- Activity Resource Requirements – what is needed for each task

- Resource Breakdown Structure (RBS) – tree of resources grouped by type

- Updated calendars and documents

### Process 5 – Estimate Activity Durations

Goal: Estimate how long each task will take.

Software Challenges:

- Software is not physical, so harder to estimate

- Developer productivity varies wildly (10x difference)

- Requirements often change

- New technologies have no history

- Team skills may be unknown

- Bugs found later can delay tasks

- Integration problems (e.g., using both old systems and new tools)

Inputs:

- Schedule Plan

- Activity info

- Resource availability

(The document cuts off here, but the next steps would continue with Developing and Controlling the Schedule.)

### Process 6 – Develop Schedule

Goal:
Build the project schedule by analyzing the tasks, their order, time estimates, resources, and constraints. In software projects, this schedule is updated often due to changes and customer feedback.

Inputs:

- Schedule Plan, Activity List & Attributes

- Network Diagram

- Resource Info & Duration Estimates

- Scope Statement

- Risk Register

- Team Assignments & Resource Breakdown Structure (RBS)

- Enterprise/Organizational factors

Tools & Techniques:

- Schedule Network Analysis:
Analyze how activities link together and impact timing.

- Critical Path Method (CPM):

  - Calculates:

    - ES (Early Start), EF (Early Finish),

    - LS (Late Start), LF (Late Finish)

  - The Critical Path is the longest path — it determines the minimum time the project will take.

  - If float = 0 ⇒ task is critical.

  - Free Float = delay allowed without affecting the next task.

🔎 Example: If task B starts only after task A finishes, and task A delays 2 days, then task B (and the project) delays too if it’s on the critical path.

- Critical Chain Method (CCM):

  - Adds resource limits to the schedule.

  - Buffers are added:

    - Project Buffer at the end to absorb delay.

    - Feeding Buffers between critical and non-critical paths.

    - Resource Buffers to ensure people/tools are ready.

  - Buffers are added intentionally, unlike float, which is a result of path analysis.

📌 Project Buffer Rule: Typically 50% of the safety time removed from task estimates.

- Resource Optimization:

  - Leveling: Shift tasks to avoid overusing resources. Might delay the schedule.

  - Smoothing: Adjust timing within float. Schedule remains unchanged.

- Modeling:

  - What-if scenarios – test different cases.

  - Monte Carlo simulation – run 100s of simulations to find best/worst case outcomes.

- Schedule Compression:

  - Crashing: Add people/resources. May increase cost.

    - Example: Hiring extra testers for faster QA.

  - Fast-Tracking: Do tasks in parallel. Higher risk of mistakes.

    - Example: Start coding before design is finalized.

  - ⚠ Brooks’ Law: Adding people late to a project slows it down after a point (>25% compression often fails).

- Incremental Product Planning / Backlog Grooming:

  - Agile teams plan product features for each sprint, refine backlog continuously.

- Scheduling Tools:

  - Gantt charts, PM software (like MS Project, Jira), network diagramming tools.

Outputs:

- Schedule Baseline: Official, approved timeline.

- Project Schedule: May be shown as Gantt chart, milestone chart, or network diagram.

- Schedule Data: Includes assumptions, constraints, and options.

- Project Calendars: Shows working days, team availability.

- Plan/Document Updates: Adjust plans based on final schedule.

### Process 7 – Control Schedule

Goal:
Monitor the actual progress, adjust as needed, and keep everything aligned with the plan.

Challenges in Software:

- Velocity (speed of delivery in Agile)

- Work-in-Progress (WIP) bottlenecks

- Risks, bugs, and changing requirements

Inputs:

- Project Plan

- Project Schedule

- Work Performance Data

- Calendars

- OPAs, Schedule Data

Tools & Techniques:

- Performance Reviews:

  - Analyze progress trends and delays.

- CPM/CCM Recalculation:

  - Recheck critical path/chain after changes.

- Earned Value Management (EVM):

  - SPI (Schedule Performance Index) = EV ÷ PV

    - SPI < 1 ⇒ behind schedule

  - SV (Schedule Variance) = EV - PV

    - SV < 0 ⇒ negative delay

- Agile Tools:

  - Burn-up/down charts, Kanban boards, Cumulative-flow diagrams

  - Retrospectives after each sprint to review what went well or wrong.

- Resource Adjustments & Modeling:

  - Use optimization, modeling, and lead/lag shifts to stay on track.

Outputs:

- Work Performance Info

- Forecasts (e.g., when project might really end)

- Change Requests

- Updates to plans and organizational documents

### Key Concepts & Examples

- Effort vs. Value:
Even high-effort tasks are useful only if they deliver value.
🔎 Example: A feature launched after the marketing campaign is wasted effort.

- Leads, Lags & Float Example:

  - Two walls (A & B) are built at the same time.

  - B starts 2 days after A to learn from A → this is a Lag.

  - If B started before A finishes → it’s a Lead.

  - Float = LS - ES = LF - EF

    - This is how much delay is allowed without delaying the project.

- Buffer Placement Example:

  - Imagine a path: Start → C → D → E → F → End

  - Add:

    - Feeding Buffer before C (if it depends on something else)

    - Resource Buffer near D (if a rare skill is needed)

    - Project Buffer after F

### Presentation Formats for Schedules

- Activity Lists – every task

- Gantt Charts – bar chart timeline

- Network Diagrams – flow of task dependencies

- Master vs. Detail Schedules – big picture vs. sprint-level

- Release Plans – Agile feature delivery roadmap

- Resource Histograms – show workload by person/team

### Math & Stats References

- PERT (Program Evaluation Review Technique):

  - Triangular & Beta formulas used for uncertain time estimates.

- Float/Slack: Time you can delay without impact.

- EVM Metrics:

  - SPI (EV ÷ PV)

  - SV (EV - PV)

### Ethical, Philosophical & Practical Implications

- Over-compression risks burnout and poor quality.

- Brooks’ Law: “Adding more people to a late project makes it later.”

- Safety/Cyber-Security must be scheduled properly, not rushed.

- Buffer management should be transparent (not hidden padding).

- Portfolio-Level Scheduling: Think beyond one project — optimize for entire organization.

### Connections to Other Knowledge Areas

- Scope Management: Changes in features change tasks/time.

- Risk Management: Affects timelines, especially with simulations (Monte Carlo).

- Resource Management: Staff availability impacts schedule paths.

- Agile/Lean Practices:

  - On-demand work (Kanban)

  - Small tasks

  - Measured with velocity

### Real-World Examples

- SAIV Case: Public website must launch before a global event.

- Structured Case: Software for a medical device — strict deadlines and legal constraints.

- Fast Tracking Risk: Starting dev work before design reviews are done could lead to major rework later.